## Slide 1: Timeline Planning and Expectation Management
Health Data Analytics · Week 11 Management Seminar
Notes: Management seminar for week 11: Timeline Planning and Expectation Management. We will go through basics and terminology, best practices for data analytics, and common pitfalls and how to avoid them. Provide opening remarks here.

## Slide 2: Basics: planning terms
Work breakdown: tasks, dependencies, milestones
Critical path: the chain that sets the end date
Estimates are ranges, not points
Expectations: what, when and how good
Notes: A work breakdown structure lists every task. Dependencies show which tasks wait on others (data access before analysis, QA before release). The critical path is the longest chain of dependent tasks; delays on it delay the project.

## Slide 3: Best practices: plan realistically
Include data access, QA and review time
Add buffer for unknowns
Set milestones stakeholders can see
Estimate from past projects
Notes: Analysts tend to estimate only the analysis. In healthcare, data access, data cleaning and stakeholder review often take longer than the modeling. Data surprises are the norm, so buffer is not padding.

## Slide 4: Best practices: manage expectations
Share status regularly, good news or bad
Flag risks early, with options
Re-baseline when scope changes
Commit to what you can deliver
Notes: "We can deliver the core analysis by the 15th, or add the subgroup breakdown by the 30th" gives the stakeholder a real choice. A changed scope needs a changed timeline, agreed in writing.

## Slide 5: Common pitfalls and how to avoid them
Optimistic estimates → use ranges and past actuals
Hidden dependencies → map IT and data owners in the plan
Late bad news → raise risks as soon as known
Notes: The planning fallacy is real: people underestimate their own tasks even when they know similar tasks ran long. Dependencies on other teams are the most common source of delay.

## Slide 6: More pitfalls and how to avoid them
New asks with no trade-off → agree on what moves
Status on activity only → report milestones and risks
Deadline set before scope → scope first, then commit
Notes: "We worked on the model" says little; "the model is validated; the deck is at risk because finance data is late" lets a sponsor act. A date promised before the work is understood is a guess.

## Slide 7: Discussion
Recall a project that ran late. What was on its critical path, and how would you plan and communicate it differently now?
Draw on your own experience and career, and apply today's seminar to that setting.
Notes: Give students a few minutes to write an answer drawn from their own experience and career, then ask two or three to share. Connect their examples back to this seminar's content. In an online section, post the same question to the discussion board.