## Slide 1: Week 2: Components of a Data Analytics Project
Health Data Analytics · Week 2 Management Seminar
Notes: Management seminar for week 2: Components of a Data Analytics Project. We will go through basics and terminology, best practices for data analytics, and common pitfalls and how to avoid them. Provide opening remarks here.

## Slide 2: Basics: anatomy of an analytics project
Business question and the decision it informs
Stakeholders: sponsor, users, data owners, experts
Requirements, data, analysis, QA, deliverable
Phases: intake, scoping, build, review, handoff
Notes: Every project, from a one-day ad hoc request to a six-month model build, has the same parts. Frameworks such as CRISP-DM (business understanding, data understanding, data preparation, modeling, evaluation, deployment) name the same idea: the technical work sits between understanding the business problem and getting the result used.

## Slide 3: Best practices: start with the decision
Write the question as a decision someone will make
Confirm the data exists before promising answers
Agree on definitions up front (member, visit, rate)
Size the work: hours, data access, review time
Notes: "How many readmissions did we have?" becomes "Should we expand the transitional care program to the second hospital?" The second version tells you what to measure, for whom, and what level of certainty is needed. Checking data availability during scoping avoids promising an answer the data can't support.

## Slide 4: Best practices: build in checkpoints
Share a mock-up of the deliverable early
Review interim numbers with a subject expert
Keep code, queries and notes in version control
Plan the handoff: who maintains this next year?
Notes: A sketch of the final table or chart at kickoff catches misunderstandings when they are cheap to fix. A revenue cycle or clinical expert will spot an implausible number faster than any test. Projects that will recur need an owner and documentation from the start.

## Slide 5: Common pitfalls and how to avoid them
Vague question → restate it as a decision; get sign-off
Data access delays → request access during scoping
No clear user → name the person who will act on it
Notes: Data access in healthcare often takes weeks because of privacy reviews and data use agreements, so start the request on day one. An analysis without a named user tends to end up unused, however good it is.

## Slide 6: More pitfalls and how to avoid them
Scope creep → log changes and re-agree on the timeline
QA skipped under deadline → schedule QA as its own phase
Scripts no one can rerun → document and parameterize
Notes: Small additions add up; a change log makes the trade-off visible. When deadlines tighten, QA is the first thing cut and the most expensive thing to have skipped. Hard-coded dates and file paths turn next quarter's rerun into a new project.

## Slide 7: Discussion
Think of a data request you've made or received. How would you restate it as a decision, and who would act on the answer?
Draw on your own experience and career, and apply today's seminar to that setting.
Notes: Give students a few minutes to write an answer drawn from their own experience and career, then ask two or three to share. Connect their examples back to this seminar's content. In an online section, post the same question to the discussion board.